## Ticket Board
Ticket ID | Date | Epic | Type | Priority | Status | Title | Problem | Description | Acceptance Criteria | Outcome | Assignee | Ownership Level | Sprint
LOG-001 | May 2026 | Logistics Performance | Investigation | High | Done | Investigate root causes of logistics dashboard slowness | Users experience slow dashboard rendering and interactions. | Conduct a comprehensive audit of the logistics application to identify performance bottlenecks in data model design, aggregations, expressions, and visualizations. | 1. Audit all application expressions and data model joins 2. Profile slow tabs and identify heavy calculations 3. Document all bottlenecks with severity ratings 4. Produce optimization recommendations report | Performance bottlenecks documented and prioritized. | Brempong | Lead Implementer | BLY — May/Jun 2026
LOG-002 | May 2026 | Logistics Performance | Story | High | Done | Implement pre-aggregated delivery metrics framework | Delivery metrics computed repeatedly at runtime cause performance degradation. | Transfer aggregation of delivery numbers to the V3 dashboard architecture. Build pre-aggregated structures and ensure fields come from aggregated tables instead of raw datasets. | 1. Transfer delivery-number aggregations to V3 architecture 2. Create pre-aggregated delivery metric tables 3. Update dashboard fields to reference aggregated sources 4. Validate KPI parity with previous implementation | Reduced dashboard processing time; aggregated structures serving all delivery metrics. | Brempong | Lead Implementer | BLY — May/Jun 2026
LOG-003 | May 2026 | Logistics Performance | Story | High | Done | Refactor dashboard visualizations to use aggregated data sources | Visualizations continue to pull from raw datasets despite availability of optimized aggregated tables. | Replace all eligible fields with aggregated-table equivalents across the V3 dashboard. Remove unused fields and update table structures accordingly. | 1. Inventory all fields still reading from raw dataset 2. Replace each with aggregated-table equivalent 3. Remove unused fields and update downstream joins 4. Run performance comparison before/after | Improved dashboard responsiveness; no visualizations reading from raw dataset. | Brempong | Primary Developer | BLY — May/Jun 2026
LOG-004 | May 2026 | Logistics Performance | Bug | High | Done | Resolve KPI count discrepancies between shipment keys and delivery numbers | Shipment counts differ between dashboard KPIs and pre-aggregated calculations. | Investigate differences between Shipment Key counting and Delivery Number counting methodologies. Align KPI variables to use consistent counting logic. | 1. Document both counting methodologies 2. Identify root cause of discrepancy 3. Align dashboard KPI variables to single consistent logic 4. Validate corrected counts with stakeholders | Consistent KPI calculations across all dashboard views. | Brempong | Lead Implementer | BLY — May/Jun 2026
LOG-005 | May 2026 | Logistics Performance | Story | Medium | Done | Refactor dashboard logic after primary-key changes | Primary-key changes in the underlying data model break existing dashboard joins and write-back relationships. | Update dashboard logic to reflect new primary keys. Modify downstream joins, adjust write-back table relationships, remove unused fields, and update table structures. | 1. Map all affected joins to the new primary key 2. Update write-back table relationships 3. Remove deprecated fields 4. Validate all dashboard pages post-refactor | Dashboard fully functional with new primary-key schema. | Brempong | Primary Developer | BLY — May/Jun 2026
DQ-001 | May 2026 | Data Quality | Story | High | Done | Build updated waybill change-tracking framework | Business users cannot identify which waybills have been modified. | Implement change-tracking indicators for edited waybills. Add highlighting for changed/updated waybills in the dashboard and maintain writeback scripts. | 1. Implement waybill change flags in writeback script 2. Add dashboard highlighting for updated waybills 3. Test highlighting logic for edge cases (multi-edit, re-edit) 4. Validate with stakeholders: 'you can validate it in the script and the dashboard' | Users can visually identify modified waybills; writeback script stores edit history correctly. | Brempong | Owner / Maintainer | BLY — May/Jun 2026
DQ-002 | May 2026 | Data Quality | Story | Medium | Done | Refactor writeback table keys to support new logistics requirements | Existing writeback tables do not support new logistics business requirements after primary-key changes. | Update writeback tables to use newly defined composite primary keys. Modify dependent joins and validate against existing data. | 1. Define new composite primary key schema 2. Update writeback table DDL 3. Modify all dependent joins 4. Run validation testing against existing records | Writeback tables fully aligned with new logistics data model. | Brempong | Owner / Maintainer | BLY — May/Jun 2026
DQ-003 | May 2026 | Data Quality | Bug | High | Done | Investigate and fix data transformation failures from schema changes | Transformation scripts fail due to missing or renamed fields (e.g. Field 'ETA_Estimated_Delivery' not found). | Identify schema changes between source and transformation layer. Update affected transformation logic and validate outputs. | 1. Identify all missing/renamed fields causing failures 2. Trace each field to its new source location 3. Update transformation scripts 4. Validate field 'ETA_Estimated_Delivery' and all other affected fields are correctly resolved | Transformation pipeline runs without schema errors; all fields correctly mapped. | Brempong | Data Engineer | BLY — May/Jun 2026
AUTO-001 | Jun 2026 | Qlik Automation | Story | High | Done | Develop logistics monitoring automations | Manual monitoring of logistics pipelines creates operational overhead and delays in detecting failures. | Build automated monitoring workflows for logistics dashboards and pipelines. Include scheduled runs, alerting logic, and deployment to production. | 1. Design automation workflow structure 2. Build scheduled monitoring automations 3. Implement alerting logic for failures 4. Validate automations run on schedule 5. Promote to production | Production-ready automation pipeline monitoring logistics datasets. | Brempong | Automation Engineer | BLY — May/Jun 2026
AUTO-002 | Jun 2026 | Qlik Automation | Task | High | Done | Promote logistics automation to production | Automation workflows validated in development are not yet available in production. | Validate and deploy all logistics automation workflows to the production Qlik environment. Pause any in-progress dev automations before promotion. | 1. Pause all dev-environment automations created during development 2. Validate promotion checklist 3. Deploy to production Qlik environment 4. Confirm production automations running on schedule | All logistics automations live and running in production. | Brempong | Automation Engineer | BLY — May/Jun 2026
AUTO-003 | Jun 2026 | Qlik Automation | Story | Medium | In Progress | Develop bookings and quotes automation framework | Bookings and Quotes processes lack automated monitoring, creating manual toil and risk of undetected failures. | Create reusable automation workflows for Bookings and Quotes datasets. Include refresh validation checks and notification logic. | 1. Map Bookings and Quotes refresh dependencies 2. Build monitoring automation workflows 3. Implement refresh validation checks 4. Add notification logic for failures 5. Test end-to-end before production promotion | Automated monitoring covering Bookings and Quotes pipelines. | Brempong | Automation Engineer | BLY — May/Jun 2026
AUTO-004 | Jun 2026 | Qlik Automation | Bug | High | Done | Investigate and fix pipeline refresh failures | Bookings and logistics pipelines fail due to refresh validation issues. | Analyze refresh validation logic and implement appropriate warning or failure behavior. Trace root cause of failures. | 1. Reproduce refresh failure conditions 2. Trace validation logic to root cause 3. Implement corrected warning/failure behavior 4. Validate fix across affected pipelines | Reliable pipeline monitoring with correct failure detection. | Brempong | Primary Investigator | BLY — May/Jun 2026
GOV-001 | Jun 2026 | Refresh Governance | Investigation | Medium | Done | Investigate dashboard refresh timestamp inconsistencies | Different dashboards display inconsistent refresh timestamps — values change unexpectedly under filtering conditions. | Review timestamp calculations and filtering behavior across implementations. Identify why TOTAL aggregation differs from filtered values. Propose and implement a fix. | 1. Document current timestamp implementations across dashboards 2. Reproduce the TOTAL vs filtered discrepancy 3. Identify root cause in aggregation logic 4. Propose standardized fix 5. Implement and validate | Root cause documented; standardized refresh timestamp logic implemented. | Brempong | Primary Investigator | BLY — May/Jun 2026
GOV-002 | Jun 2026 | Refresh Governance | Story | Medium | Done | Standardize refresh time calculation logic across dashboards | Dashboard refresh timestamps change unexpectedly under filtering conditions due to non-global aggregation expressions. | Implement standardized refresh logic using global aggregation expressions that are filter-independent. | 1. Define global aggregation expression standard for refresh timestamps 2. Apply standard to all affected dashboards 3. Test under multiple filter combinations 4. Document the standard for future dashboards | Consistent, filter-independent refresh-time reporting across all dashboards. | Brempong | Primary Developer | BLY — May/Jun 2026
ADM-001 | Jun 2026 | Platform Admin | Investigation | Medium | Done | Audit Slack notification architecture in Qlik automations | Team lacks understanding of how Slack integrations work within the Qlik automation environment — unclear which automations use webhooks vs OAuth. | Review all Slack-related automations in Amalitech's Qlik space. Determine integration mechanisms, document connector architecture, and identify whether webhook URLs exist. | 1. Audit all automations in Amalitech's Qlik space for Slack integrations 2. Classify each as webhook-based or OAuth-based 3. Document connector architecture 4. Identify ownership and configuration of each integration 5. Produce findings report with recommendations | Complete architecture inventory of Slack integrations in Qlik; integration ownership documented. | Brempong | Technical Lead for Investigation | BLY — May/Jun 2026
ADM-002 | Jun 2026 | Platform Admin | Documentation | Low | Done | Document Qlik automation integrations and ownership | Integration ownership and configurations for Slack, automations, schedules, and notification flows are not fully documented. | Create comprehensive documentation covering all Qlik automation integrations, connector configurations, schedule ownership, and notification flows. | 1. Document all Slack integration configurations 2. Document automation schedules and owners 3. Document notification flow architecture 4. Review with team for completeness 5. Publish to shared knowledge base | Full integration documentation available to team; reduces knowledge-silo risk. | Brempong | Technical Lead for Investigation | BLY — May/Jun 2026
DOC-001 | Jun 2026 | Documentation | Story | Medium | Done | Validate BLY MDM documentation against live implementation | Existing MDM documentation may not accurately represent the deployed implementation — undocumented gaps risk onboarding and audit failures. | Perform validation of BLY MDM documentation against deployed environments and configurations. Generate a validation report (BLY_MDM_Validation_Report.md) documenting gaps. | 1. Review existing MDM documentation end-to-end 2. Cross-reference against deployed configuration 3. Identify all discrepancies and gaps 4. Generate BLY_MDM_Validation_Report.md 5. Share findings with stakeholders | Validated MDM documentation with gap analysis; stakeholders informed of discrepancies. | Brempong | Documentation Owner | BLY — May/Jun 2026
DOC-002 | Jun 2026 | Documentation | Task | Low | To Do | Establish repeatable documentation validation process | No standardized documentation review process exists — validation is done ad-hoc and inconsistently. | Create a repeatable documentation validation framework. Define checklist, review cadence, ownership, and output format. | 1. Define documentation validation checklist 2. Set review cadence (e.g. per sprint / per release) 3. Assign ownership roles 4. Define output format (e.g. validation report template) 5. Pilot on next documentation asset | Standardized, repeatable documentation validation process adopted by team. | Brempong | Documentation Owner | BLY — May/Jun 2026
DEVOPS-001 | Jun 2026 | DevSecOps | Story | High | Done | Design secure AWS VPC architecture with public and private subnet segmentation | Infrastructure lacked a secure, segmented network — all resources would be co-located without isolation. | Design a VPC with separate public and private subnets across availability zones. Apply correct CIDR block allocation and document the architecture before deployment. | 1. Define VPC CIDR block 2. Design public and private subnet CIDR ranges 3. Plan AZ distribution for resilience 4. Document architecture diagram 5. Validate design against security best practices (public/private separation) | Secure VPC architecture documented and approved for deployment. | Brempong | Lead Implementer | AWS DevSecOps Project
DEVOPS-002 | Jun 2026 | DevSecOps | Story | High | Done | Provision VPC and configure public/private subnets | No cloud network existed — infrastructure had nowhere to run. | Create the VPC in AWS and provision both public and private subnets with correct CIDR allocations. | 1. Create VPC with defined CIDR block 2. Create public subnet with appropriate CIDR 3. Create private subnet with appropriate CIDR 4. Assign subnets to correct availability zones 5. Verify subnet routing table associations | VPC live with correctly segmented public and private subnets. | Brempong | Primary Developer | AWS DevSecOps Project
DEVOPS-003 | Jun 2026 | DevSecOps | Story | High | Done | Deploy and configure Internet Gateway for public subnet resources | Public subnet resources require internet access — no IGW existed. | Deploy and attach an Internet Gateway to the VPC. Configure public subnet route tables to route internet-bound traffic through the IGW. | 1. Create and attach IGW to the VPC 2. Update public subnet route table to add 0.0.0.0/0 → IGW route 3. Verify internet connectivity from a public subnet resource 4. Document routing configuration | Public resources can reach the internet; routing validated. | Brempong | Primary Developer | AWS DevSecOps Project
DEVOPS-004 | Jun 2026 | DevSecOps | Story | High | Done | Configure NAT Gateway for secure outbound access from private resources | Private subnet resources require outbound internet access without becoming publicly accessible. | Deploy a NAT Gateway in the public subnet and configure private subnet route tables to route outbound traffic through it. | 1. Deploy NAT Gateway in public subnet 2. Allocate Elastic IP for NAT Gateway 3. Update private subnet route table: 0.0.0.0/0 → NAT Gateway 4. Test outbound internet access from a private resource 5. Confirm private resource has no inbound public exposure | Private resources can reach the internet outbound; no public inbound exposure. | Brempong | Primary Developer | AWS DevSecOps Project
DEVOPS-005 | Jun 2026 | DevSecOps | Story | High | Done | Provision EC2 instances within designed network architecture | Infrastructure required compute resources for VPN and internal services — no EC2 instances existed. | Launch and configure EC2 instances within the designed VPC. Place public-facing instances (e.g. Pritunl VPN) in the public subnet and internal services in the private subnet. Configure security groups appropriately. | 1. Launch EC2 instance in public subnet (VPN host) 2. Launch EC2 instance in private subnet (internal services) 3. Configure security groups: allow only required ports 4. Assign key pairs for SSH access 5. Verify connectivity within the network | EC2 instances running in correct subnets with appropriate security group configurations. | Brempong | Primary Developer | AWS DevSecOps Project
DEVOPS-006 | Jun 2026 | DevSecOps | Story | Medium | Done | Configure route tables and validate traffic flow across network segments | Network traffic required controlled routing between public, private, and internet resources — unvalidated routing creates security and connectivity gaps. | Configure and validate route tables for both public and private subnets. Ensure traffic flows correctly: internet → public subnet via IGW; private subnet → internet via NAT; private → private directly. | 1. Document expected traffic flows for all subnet pairs 2. Verify public route table: internet route via IGW 3. Verify private route table: outbound route via NAT Gateway 4. Test internal routing between public and private subnets 5. Document final routing configuration | All traffic flows validated; routing tables documented. | Brempong | Primary Developer | AWS DevSecOps Project
DEVOPS-007 | Jun 2026 | DevSecOps | Story | High | Done | Deploy Pritunl VPN server infrastructure in public subnet | Users required secure access to private subnet resources — no VPN infrastructure existed. | Deploy and configure Pritunl VPN server on the public subnet EC2 instance. Configure server settings, user authentication, and VPN profiles. | 1. Install Pritunl on public EC2 instance 2. Configure Pritunl server settings 3. Set up user authentication 4. Generate VPN organization and server in Pritunl dashboard 5. Attach server to correct network interface and port 6. Verify server is reachable from the internet | Pritunl VPN server live and accepting authenticated connections. | Brempong | Lead Implementer | AWS DevSecOps Project
DEVOPS-008 | Jun 2026 | DevSecOps | Story | High | Done | Configure Pritunl client access and validate private subnet connectivity | Users were unable to access resources located within private subnets — no client VPN profiles existed. | Configure client VPN profiles in Pritunl and validate that connected clients can reach private subnet resources. | 1. Create Pritunl user accounts 2. Generate client VPN profiles 3. Configure client with profile (Pritunl client app) 4. Connect and verify IP assignment within VPN range 5. Test connectivity to private subnet resources from connected client | Client profiles generated; VPN access validated; private subnet resources reachable through VPN only. | Brempong | Lead Implementer | AWS DevSecOps Project
DEVOPS-009 | Jun 2026 | DevSecOps | Story | High | Done | Validate end-to-end secure connectivity through VPN to private resources | Private resources must be accessible only through approved VPN channels — unvalidated access controls are a security risk. | Perform end-to-end testing of VPN access to private subnet resources. Validate that direct (non-VPN) access to private resources is blocked, and that VPN-connected clients have correct access. | 1. Test connectivity from VPN-connected client to private subnet resource — expect success 2. Test direct internet connectivity to private subnet resource — expect failure 3. Validate security group rules are enforcing intended access controls 4. Document test results and security validation findings 5. Produce final infrastructure documentation | End-to-end secure connectivity validated; direct public access to private resources confirmed blocked. | Brempong | Lead Implementer | AWS DevSecOps Project

## Career Milestones
Career Milestones — Brempong Appiah Dankwah ¦ Boart Longyear ¦ May–Jun 2026
7 first-of-kind milestones across Analytics Engineering, Data Quality, Automation, Governance & Platform Operations
ID | Milestone | Date | Career Impact / Role Unlocked | Why It Matters | Key Deliverables | Related Tickets
M-1 | First BI Performance Engineering Project | May 2026 | Analytics Engineer | Moved beyond dashboard creation into query optimization, data model redesign, aggregation engineering, and performance auditing. Took full ownership of diagnosing and fixing dashboard slowness for an enterprise logistics application. | • Conducted full Qlik application performance audit • Designed and implemented pre-aggregated delivery metric framework • Transferred aggregations to V3 dashboard architecture • Resolved KPI count discrepancies between shipment keys and delivery numbers | LOG-001, LOG-002, LOG-003, LOG-004
M-2 | First Enterprise Dashboard Modernization Initiative | May 2026 | Analytics Engineer / BI Engineer | Led improvements to dashboard architecture following primary-key changes — handling downstream impact across joins, write-back relationships, and field inventories. Delivered production-grade refactored dashboards. | • Refactored dashboard logic to align with new primary-key schema • Modified write-back table relationships and downstream joins • Removed deprecated fields and updated table structures • Validated all pages post-refactor | LOG-005
M-3 | First Data Quality Ownership Role | May 2026 | Data Quality Engineer | Became the owner of write-back systems and change-tracking logic for logistics data. Maintained data quality writeback scripts, implemented waybill change highlighting, and resolved schema-change-driven transformation failures. | • Built waybill change-tracking framework with dashboard indicators • Maintained writeback scripts for edited-waybill storage • Investigated and fixed field 'ETA_Estimated_Delivery' schema failure • Refactored writeback table keys for new business requirements | DQ-001, DQ-002, DQ-003
M-4 | First Automation Engineering Initiative | Jun 2026 | Platform Automation Engineer | Entered platform engineering by building, managing, and deploying Qlik automations for logistics monitoring. Developed automation frameworks for Bookings and Quotes. Investigated pipeline refresh failures. | • Built and deployed logistics monitoring automations to production • Managed pipeline schedules — paused/promoted automations • Investigated and fixed pipeline refresh validation failures • Started Bookings & Quotes automation framework | AUTO-001, AUTO-002, AUTO-003, AUTO-004
M-5 | First Enterprise Production Support Responsibility | Jun 2026 | Production Data Engineer | Took on investigation of production refresh failures, timestamp inconsistencies, and schema discrepancies — developing incident response and root-cause analysis capabilities on live systems. | • Investigated refresh timestamp inconsistencies and identified TOTAL vs filtered discrepancy • Proposed and implemented standardized global aggregation expression for refresh logic • Diagnosed schema changes causing transformation failures • Investigated KPI data discrepancies in production dashboards | GOV-001, GOV-002, DQ-003
M-6 | First Platform Governance Investigation | Jun 2026 | Data Governance / Platform Admin | Audited the Qlik platform's Slack integration architecture — determining whether webhook URLs existed, classifying OAuth vs webhook-based integrations, and documenting connector ownership. First exposure to platform governance. | • Audited all automations in Amalitech's Qlik space for Slack integrations • Classified integrations as webhook-based or OAuth-based • Documented connector architecture and ownership • Produced findings report and architecture documentation | ADM-001, ADM-002
M-7 | First Technical Documentation Governance Initiative | Jun 2026 | Data Governance / Documentation Owner | Performed validation of BLY MDM documentation against the live implementation. Generated BLY_MDM_Validation_Report.md and shared findings with stakeholders. Initiated the design of a repeatable documentation validation process. | • Validated MDM documentation against deployed environment • Identified and documented all discrepancies and gaps • Produced and shared BLY_MDM_Validation_Report.md • Initiated design of repeatable documentation validation framework | DOC-001, DOC-002
DevSecOps — AWS Infrastructure Project ¦ Jun 2026
M-8 | First Cloud Networking Implementation | Jun 2026 | Cloud / Network Engineer | Designed and deployed a complete AWS network from scratch — VPC, public and private subnets, Internet Gateway, NAT Gateway, and route tables. First time owning cloud networking infrastructure end-to-end rather than consuming it. | • Designed VPC CIDR and subnet architecture • Provisioned public and private subnets • Deployed and configured Internet Gateway • Deployed NAT Gateway for private outbound access • Configured route tables for all traffic flows | DEVOPS-001, DEVOPS-002, DEVOPS-003, DEVOPS-004, DEVOPS-006
M-9 | First Infrastructure Deployment Project | Jun 2026 | Infrastructure / Platform Engineer | Instead of consuming cloud infrastructure built by others, took ownership of provisioning it — launching EC2 instances, configuring security groups, and validating network connectivity across a multi-subnet AWS environment. | • Launched EC2 instances in public and private subnets • Configured security groups with least-privilege rules • Assigned key pairs and validated SSH access • Verified compute connectivity within the VPC | DEVOPS-005
M-10 | First VPN Infrastructure Deployment | Jun 2026 | Network Security Engineer | Deployed and fully configured Pritunl VPN infrastructure — server installation, authentication setup, profile generation, and client connectivity validation. First hands-on experience with enterprise VPN technology. | • Installed and configured Pritunl VPN server on EC2 • Set up user authentication and VPN organization • Generated client VPN profiles • Validated client connectivity to private subnet resources | DEVOPS-007, DEVOPS-008
M-11 | First Security-Oriented Infrastructure Design | Jun 2026 | DevSecOps / Security Engineer | Applied security-by-design principles to infrastructure — deliberately separating public and private network segments, enforcing VPN-only access to private resources, and validating that direct public access was blocked. First exposure to infrastructure security architecture thinking. | • Designed public/private network segmentation • Enforced VPN-only access to private subnet resources • Validated security groups enforcing intended access controls • Confirmed direct public access to private resources is blocked | DEVOPS-009
M-12 | First DevSecOps Foundation Established | Jun 2026 | DevSecOps Engineer | Completed a full hands-on DevSecOps learning cycle — from VPC design through to end-to-end connectivity validation. Gained practical exposure to secure infrastructure architecture, least-privilege access, and network segmentation that underpins enterprise cloud security. | • Designed and built secure AWS infrastructure end-to-end • Applied least-privilege access and network segmentation principles • Validated security controls through structured testing • Produced infrastructure documentation • Expanded role scope: Data Engineer → Platform/DevSecOps Engineer exposure | DEVOPS-001–009

## Skills Acquired
Skills Acquired — Brempong Appiah Dankwah ¦ Boart Longyear ¦ May–Jun 2026
Domain | Skill Category | Specific Skills | Proficiency Level | Evidence (Tickets) | Resume Bullet
Data Engineering | ETL & Transformation | • Data transformation design • Schema evolution management • Field mapping & join design • Pipeline troubleshooting • Handling missing/renamed fields | Practitioner | DQ-003, LOG-002, LOG-003 | Designed and maintained ETL transformation logic across logistics datasets, managing schema evolution and resolving pipeline failures caused by renamed fields.
Data Engineering | Data Quality Engineering | • Writeback system ownership • Change-record tracking • Write-back table key management • Root-cause analysis • Data validation workflows | Owner | DQ-001, DQ-002, DQ-003 | Owned data quality writeback processes including change tracking, composite key refactoring, and validation workflows for a logistics reporting platform.
Analytics Engineering | Dashboard Performance Optimization | • Pre-aggregation strategy design • Aggregated data model architecture • KPI expression engineering • Field inventory & dead-field removal • Performance profiling | Lead | LOG-001, LOG-002, LOG-003 | Implemented pre-aggregated data models and refactored dashboard field sources to eliminate raw-dataset reads, materially improving Qlik dashboard performance.
Analytics Engineering | Qlik Sense Development | • Qlik data model design • Set analysis & KPI expressions • Writeback implementation • Dashboard refactoring • V3 architecture patterns • Dashboard performance auditing | Lead | LOG-001–LOG-005, DQ-001–DQ-003 | Led enterprise Qlik Sense dashboard development including data model design, KPI engineering, writeback implementation, and V3 architecture migration for logistics reporting.
Platform Engineering | Qlik Automation Development | • Automation workflow design • Scheduled pipeline orchestration • Pause/promote automation management • Refresh validation logic • Alerting & notification design | Practitioner | AUTO-001, AUTO-002, AUTO-003, AUTO-004 | Built and deployed Qlik monitoring automations for logistics pipelines, including scheduling, refresh validation, and failure alerting logic.
Platform Engineering | Pipeline Monitoring & Observability | • Refresh failure investigation • Timestamp inconsistency diagnosis • Monitoring design • Health check implementation • Pipeline reliability improvement | Practitioner | AUTO-004, GOV-001, GOV-002 | Investigated and resolved pipeline refresh failures and timestamp inconsistencies, implementing standardized global aggregation expressions for reliable monitoring.
Data Governance | Platform Administration | • Qlik automation auditing • Slack integration investigation • OAuth vs webhook classification • Connector ownership mapping • Integration architecture documentation | Emerging | ADM-001, ADM-002 | Conducted platform-level audit of Slack notification integrations within Qlik, classifying integration mechanisms and documenting connector ownership across automations.
Data Governance | Metadata & Documentation Governance | • Documentation validation methodology • Gap analysis • Validation report authoring • Process design for repeatable reviews • Stakeholder communication of findings | Emerging | DOC-001, DOC-002 | Validated BLY MDM documentation against the deployed environment, produced a gap-analysis report (BLY_MDM_Validation_Report.md), and initiated a repeatable documentation validation process.
Production Operations | Incident Response & Root-Cause Analysis | • Production debugging methodology • Failure reproduction • Root-cause tracing • Schema-change impact assessment • Stakeholder communication during incidents | Practitioner | DQ-003, AUTO-004, GOV-001 | Developed production operations capability through repeated investigation of live refresh failures, schema-change regressions, and KPI discrepancies in enterprise dashboards.
Production Operations | Reliability Engineering | • Monitoring system design • Failure prevention strategies • Operational runbook thinking • Standardized implementation patterns • Cross-dashboard consistency enforcement | Emerging | GOV-002, AUTO-001, AUTO-004 | Improved dashboard and pipeline reliability by standardizing refresh logic, implementing monitoring automations, and enforcing consistent calculation patterns across dashboards.
DevSecOps — AWS Infrastructure Project ¦ Jun 2026
Cloud Infrastructure | AWS VPC & Subnetting | • AWS VPC creation and configuration • Public and private subnet design • CIDR block allocation • Availability zone distribution • Cloud architecture fundamentals | Practitioner | DEVOPS-001, DEVOPS-002 | Designed and provisioned AWS VPC with segmented public and private subnets using correct CIDR allocation and multi-AZ distribution.
Networking | Gateway & Routing Configuration | • Internet Gateway (IGW) deployment • NAT Gateway deployment • Route table creation and management • Traffic flow design • Public vs private routing patterns | Practitioner | DEVOPS-003, DEVOPS-004, DEVOPS-006 | Configured Internet Gateways, NAT Gateways, and route tables to enforce controlled traffic flows between public subnets, private subnets, and the internet.
Cloud Infrastructure | EC2 Administration | • EC2 instance provisioning • Security group configuration • Key pair management • Linux fundamentals • Instance placement in network segments | Practitioner | DEVOPS-005 | Launched and configured EC2 instances across public and private subnets with least-privilege security groups and SSH key-pair access management.
Security | VPN Infrastructure | • Pritunl VPN server deployment • VPN server configuration • User authentication setup • Client profile generation • Secure remote access design | Practitioner | DEVOPS-007, DEVOPS-008 | Deployed and configured Pritunl VPN infrastructure on AWS EC2, enabling authenticated secure user access to private subnet resources.
Security | Network Segmentation & Access Control | • Public/private network segmentation • Security-by-design principles • Least-privilege access enforcement • Security group rule design • VPN-only private resource access | Emerging | DEVOPS-001, DEVOPS-009 | Applied network segmentation and security-by-design principles to enforce VPN-only access to private infrastructure while blocking direct public exposure.
DevOps | Infrastructure Validation & Testing | • End-to-end connectivity testing • Security control validation • Network troubleshooting • Infrastructure documentation • Structured test case design | Emerging | DEVOPS-009 | Performed structured end-to-end infrastructure validation — testing VPN connectivity, verifying private resource isolation, and confirming security group enforcement.
DevSecOps | Secure Infrastructure Architecture | • Security-oriented design thinking • Separation of public/private/management networks • Private resource protection patterns • Infrastructure hardening concepts • DevSecOps principles | Emerging | DEVOPS-001–009 | Applied DevSecOps principles throughout an end-to-end AWS infrastructure deployment — designing for security from the network layer upward rather than adding security as an afterthought.

## Summary
Boart Longyear BIDM ¦ Brempong Appiah Dankwah ¦ Performance Summary ¦ May–Jun 2026
26 Total Tickets | 22 Done | 3 In Progress | 1 To Do | 6 Epics | 12 Milestones | 17 Skills Gained
Epics & Ticket Distribution
Logistics Performance | LOG-001–005 | 5 tickets | High
Data Quality | DQ-001–003 | 3 tickets | High
Qlik Automation | AUTO-001–004 | 4 tickets | High+Med
Refresh Governance | GOV-001–002 | 2 tickets | Medium
Platform Admin | ADM-001–002 | 2 tickets | Medium
Documentation | DOC-001–002 | 2 tickets | Low+Med
DevSecOps | DEVOPS-001–009 | 9 tickets | High+Med
Resume-Level Summary
• Led enterprise Qlik analytics performance optimization by implementing pre-aggregated data models, redesigning write-back workflows, refactoring dashboard field sources, and auditing performance bottlenecks across a logistics reporting application.
• Owned data quality engineering activities including writeback system maintenance, change-tracking implementation, composite key refactoring, and schema-change incident resolution across logistics datasets.
• Developed and deployed Qlik automation and monitoring pipelines for logistics, bookings, and data-quality workflows — including scheduling, refresh validation, failure alerting, and production promotion.
• Investigated and resolved production-grade incidents including refresh timestamp inconsistencies, pipeline validation failures, and KPI count discrepancies — developing root-cause analysis and reliability engineering capabilities.
• Conducted platform-level governance investigations into Qlik automation architecture and Slack integration design, producing architecture documentation and integration inventories.
• Validated and documented BLY MDM implementation, generating a gap-analysis report and initiating a repeatable documentation validation process.
• Completed hands-on DevSecOps training by designing and deploying secure AWS infrastructure comprising VPCs, public/private subnets, Internet Gateways, NAT Gateways, EC2 instances, and Pritunl VPN — enabling secure user access to private subnet resources while applying network segmentation, least-privilege access, and security-by-design principles.